## Daily Tracker
Backend Developer — Business Listing
40 Working Days · 8 Hours/Day · Fill in Date, Status, Hours, and Notes every day.
Day | Date | Week | Task / Focus for the Day | Status | Hours Worked | GitHub Commit | Notes / Blocked Reason
1 | 2026-08-25 | Week 1 | Set node/npm/nest cSet up Node, npm, and Nest CLI. Set up proper git branches, pushed the starter files. Got PostgreSQL running in Docker and connected it to Prisma. Ran the migration and got the User table created. Tested the full auth flow with curl i.e. register, login, and the protected /me route all working with JWT. Also restructured the repo into backend/ and frontend/ folders, and set up a Trello board for tracking tasks going forward.li | Complete | 8 hours | 1. chore: add starter project structure (auth module implemented; listings, reviews, bookings scaffolded) 2. chore: F11restructure repo into backend/ and frontend/ monorepo H7layout 3. chore: approve install scripts, add lockfile and initial User migration 4. chore: switch backend port to 3001 to avoid clash with frontend default 5. Removed guideline document 6. Deleted Backend-Dev5-Guideline.docx 7. docs: add daily tracker spreadsheet | Took a bit to figure out the npm script approval issue with bcrypt/prisma
2 |  |  |  | Todo
3 |  |  |  | Todo
4 |  |  |  | Todo
5 |  |  |  | Todo
6 |  | Week 2 | Homepage — build every section | Todo
7 |  |  |  | Todo
8 |  |  |  | Todo
9 |  |  |  | Todo
10 |  |  |  | Todo
11 |  | Week 3 | Inner pages (first batch) | Todo
12 |  |  |  | Todo
13 |  |  |  | Todo
14 |  |  |  | Todo
15 |  |  |  | Todo
16 |  | Week 4 | Remaining inner pages + finish the 3 required components | Todo
17 |  |  |  | Todo
18 |  |  |  | Todo
19 |  |  |  | Todo
20 |  |  |  | Todo
21 |  | Week 5 | Dashboard / modules (if applicable to this project) | Todo
22 |  |  |  | Todo
23 |  |  |  | Todo
24 |  |  |  | Todo
25 |  |  |  | Todo
26 |  | Week 6 | Interactivity, form validation, state management | Todo
27 |  |  |  | Todo
28 |  |  |  | Todo
29 |  |  |  | Todo
30 |  |  |  | Todo
31 |  | Week 7 | Wire up config for dynamic content + responsive QA | Todo
32 |  |  |  | Todo
33 |  |  |  | Todo
34 |  |  |  | Todo
35 |  |  |  | Todo
36 |  | Week 8 | Bug fixing, content polish, deployment, final presentation | Todo
37 |  |  |  | Todo
38 |  |  |  | Todo
39 |  |  |  | Todo
40 |  |  |  | Todo